## Summary
Ledgerly — remaining steps
As of October 7, 2026. Change the Status column on the Steps sheet and these counts update.
Phase | Total | Done | Left | % done
1 · Now
2 · Before launch
3 · Launch day
4 · After launch
5 · Later
All
Who | Left
You
Me
Both
How to use this
• “Me” means Claude: just ask in chat and I’ll do it.
• Work top to bottom: phase 1 can all happen now, in any order.
• Phase 2 waits on accounts (Apple, Google, Stripe activation).
• Phase 3 starts when you tell me “go live”.
• The Marketing sheet runs alongside phases 1–3.

## Steps
# | Phase | Area | Step | Who | Where / how | Why it matters | Status | Notes
1 | 1 · Now | Payments | Activate your Stripe account (business details and bank account) | You | Stripe dashboard → Activate payments | Needed before anyone can actually pay | Not started
2 | 1 · Now | Payments | Turn on customer emails: receipts, failed payments and upcoming renewals | You | Stripe → Settings → Customer emails | Customers expect receipts and warnings before a renewal | Not started
3 | 1 · Now | Payments | Talk to an accountant about sales tax and decide on Stripe Tax | You | Accountant, then Stripe → Tax | Some states tax software subscriptions | Not started
4 | 1 · Now | Legal | Choose the business name and state for the Terms (section 14) | You | Tell me and I’ll update the Terms | The Terms need a legal owner and governing state | Not started
5 | 1 · Now | Legal | Have a lawyer read the Privacy Policy and Terms | You | app.myledgerlyapp.com/privacy.html and /terms.html | Cheap insurance before taking money | Not started
6 | 1 · Now | Support | Send a test email to support@ and tell me which provider receives it | You | Your email app | Makes sure help requests reach you | Not started
7 | 1 · Now | Security | Turn on 2-step sign-in for GitHub, Supabase, Stripe, Netlify, Resend, PostHog, Cloudflare, your domain registrar and your email | You | Each service’s security settings | One stolen password could take the whole app down | Not started
8 | 1 · Now | Security | Turn on the domain transfer lock | You | Your domain registrar | Stops someone moving your domain away | Not started
9 | 1 · Now | Security | Turn on Dependabot alerts and secret scanning | You | GitHub → Ledgerly → Settings → Code security | Warns about risky packages and leaked keys | Not started
10 | 1 · Now | Security | Create Cloudflare Turnstile keys; put the site key in Netlify (VITE_TURNSTILE_SITE_KEY) and the secret in GitHub (TURNSTILE_SECRET_KEY) | You | Cloudflare → Turnstile | Blocks bots from creating accounts | Not started
11 | 1 · Now | Database | Upgrade Supabase to Pro (daily backups) and keep the Spend Cap on | You | Supabase → Billing | Free projects pause and have no daily backups | Not started
12 | 1 · Now | Database | Enforce SSL and turn on leaked-password protection | You | Supabase → Database settings and Auth → Passwords | Basic account and data protection | Not started
13 | 1 · Now | Database | Add a calendar reminder before the Supabase access token expires | You | Your calendar | Deploys fail with “Unauthorized” when it expires | Not started
14 | 1 · Now | Analytics | In PostHog, discard client IP addresses and set a billing limit | You | PostHog → Project settings and Billing | Matches the Privacy Policy and caps cost | Not started
15 | 1 · Now | Cleanup | Revoke the old OpenRouter key and delete the OPENROUTER_API_KEY and AI_ALLOWED_EMAILS secrets | You | OpenRouter, then GitHub → Settings → Secrets | Unused keys are a needless risk | Not started
16 | 1 · Now | Support | Finish Crisp: chat color, ask for email, phone app and notifications, away message, domain lock | You | Crisp → Settings → Chatbox | So you never miss a message | Not started
17 | 1 · Now | Support | Point Hugo at https://myledgerlyapp.com/help/ as its knowledge source and test the chat | You | Crisp → AI / Knowledge | Hugo answers from your real help guides | Not started
18 | 1 · Now | Support | While in test mode, include “Premium is free while we test payments” in Hugo’s text | You | Crisp → Hugo instructions | Hugo shouldn’t quote prices that aren’t live | Not started
19 | 1 · Now | Tools | Re-authorize the Ledgerly connector in claude.ai | You | claude.ai → Settings → Connectors | Lets me check your live budget data when you ask | Not started
20 | 1 · Now | App | Write the “Payment failed” and “Your plan has ended” messages | Me | Ask me | Clear next steps when a card fails | Not started
21 | 1 · Now | App | Fix the out-of-date line in docs/BILLING.md | Me | Ask me | Keeps the billing guide accurate | Not started
22 | 2 · Before launch | Testing | Read through every help guide | You | myledgerlyapp.com/help | Spot anything confusing before customers do | Not started
23 | 2 · Before launch | Testing | Sign up as a brand-new user on your phone and go through everything | You | app.myledgerlyapp.com | The best test of the first five minutes | Not started
24 | 2 · Before launch | Testing | Invite 5–10 friends or family as beta testers and collect feedback | You | Promo QR codes give them free Premium | Real people find what we can’t | Not started
25 | 2 · Before launch | Apple | Enroll in the Apple Developer Program | You | developer.apple.com/programs ($99/year) | Needed for the iPhone app | Not started
26 | 2 · Before launch | Apple | Register the App ID com.myledgerlyapp.ledgerly and create the app in App Store Connect | You | developer.apple.com and appstoreconnect.apple.com | Reserves the app and its name | Not started
27 | 2 · Before launch | Apple | Create an App Store Connect Admin API key; add GitHub secrets APPLE_TEAM_ID, ASC_KEY_ID, ASC_ISSUER_ID, ASC_KEY_P8 | You | App Store Connect → Users and Access → Integrations | Lets GitHub build and upload the app | Not started
28 | 2 · Before launch | Apple | TestFlight build, Sign in with Apple, email links that open the app, human check in the app | Me | After the Apple steps above | Gets the iPhone app ready to test | Not started
29 | 2 · Before launch | Apple | App Store listing: screenshots, description and privacy answers | Both | I draft, you submit | Required for review | Not started
30 | 2 · Before launch | Google | Create a Google Play developer account (personal or company) | You | play.google.com/console ($25 once) | Needed for the Android app | Not started
31 | 2 · Before launch | Payments | Create a restricted live Stripe key and put it in the STRIPE_SECRET_KEY secret | You | Stripe → Developers → API keys | Live payments need a live key | Not started
32 | 2 · Before launch | Payments | Remake your promo codes in live mode | You | Stripe → Products → Coupons (live) | Test-mode codes don’t work for real | Not started
33 | 2 · Before launch | Payments | Tell me “go live” | You | Chat with me | Starts the launch-day steps | Not started
34 | 3 · Launch day | Payments | Set VITE_BILLING_MODE=live and turn off counting test plans | Me | Netlify setting and a database change | Switches Premium to real payments | Not started
35 | 3 · Launch day | Payments | Remove the test-mode wording from the app, website and Terms, then deploy | Me | Ask me | No more “free while we test” | Not started
36 | 3 · Launch day | Payments | Buy Premium with your own card, check it works, then refund it | Both | App and Stripe dashboard | Proves the whole payment path | Not started
37 | 3 · Launch day | Support | Update Hugo’s text to remove the test-mode line | You | Crisp → Hugo instructions | Hugo quotes real prices | Not started
38 | 4 · After launch | Database | Check Supabase usage once a month | You | Supabase → Usage | No surprise bills or limits | Not started
39 | 4 · After launch | Email | Move DMARC to p=quarantine after 2–4 weeks of clean reports | You | Your DNS settings | Stops others faking your email | Not started
40 | 4 · After launch | Monitoring | Optional: add an uptime monitor (for example UptimeRobot) | You | uptimerobot.com (free) | Know when the site is down before users tell you | Not started
41 | 5 · Later | Ideas | Home: shorten “Where your money goes” (top five with Show all) | Me | docs/IDEAS.md | Home gets shorter on phones | Not started
42 | 5 · Later | Ideas | Adding a purchase starts on the last category used | Me | docs/IDEAS.md | Fewer purchases logged to the wrong category | Not started
43 | 5 · Later | Ideas | Smaller month picker on Transactions and Insights | Me | docs/IDEAS.md | Less space taken at the top | Not started

## Marketing
Area | Step | Who | Why | Status
Foundation | Write a one-sentence promise for Ledgerly (who it’s for and what it does better) | You | Everything else builds on this | Not started
Foundation | Pick 1–2 audiences to start with (for example couples, freelancers and small business owners using shared categories) | You | Shared categories are a real standout for business owners | Not started
Website | Add real screenshots and a short demo video to the home page | Both | People decide in seconds | Not started
Website | Add an email sign-up for launch news | Me | Build a list before the app stores open | Not started
Beta | Give beta testers free Premium with promo QR codes and ask for honest feedback | You | Feedback plus your first testimonials | Not started
Beta | Collect 3–5 quotes from testers (with permission) for the website and store listing | You | Social proof | Not started
Content | Write short posts from the help guides (for example “How to pay yourself from a business budget”) | Both | Free search traffic over time | Not started
Social | Pick one channel you enjoy (TikTok, Instagram, Reddit, YouTube) and post weekly | You | Consistency beats being everywhere | Not started
Launch | Plan a launch week: email list, social posts, Product Hunt and relevant communities | You | One focused push gets early users | Not started
Store | App Store keywords, subtitle and screenshots that show the Home page and goals | Both | Most app installs come from store search | Not started
Measure | Watch sign-ups, first budget created and Premium upgrades in PostHog each week | You | Shows what’s working (no amounts or names are tracked) | Not started